## Introduction
Welcome to the IPO Timetable!
In order to prepare the registration statement, a series of planning and review meetings ("all-hands" meetings) are held with company officials (XYZ), the company's counsel (CC), the underwriters (U) and their counsel (UC), and the company's accountants (A). A timetable for the offering is agreed on at these meetings. We have provided a typical timetable for a public offering.
| Chronological Function | Insert start date here: | 1999-01-14
Insert a start date and the IPO
Timetable will lay out all the steps
in chronological order and assign
dates to each step in the IPO process.
| Reverse Order Function | Insert closing date here: | 1999-11-14
Insert a closing date and the IPO
Timetable will show you when to
begin the IPO process and lays out
all the steps and respective dates.

## IPO Timeline
IPO Timetable
| Date | Activity | Responsibility
| 1999-01-14 | Initial organization meeting and due dilligence |  | All
Review Timetable
Review letter of intent and discuss
underwriting issues.
Discuss Underwriters' fees and compensation
Assign registration statement preparation
responsibilities
Identify accounting and other problems.
Select Printer
Review financial forecasts
|  | Management due dilligence presentations. |  | All
Discuss transfer agent and registrar.
Prepare list of parties involved (phone numbers,
addresses, secretaries, etc.) referred to as
the working group list.
| 1999-01-28 | First draft of registration statement distributed. |  | All
| 1999-02-05 | First drafting session and due dilligence. |  | All
Complete due dilligence presentations.
Review draft of registration statement
Discuss problems
| 1999-02-05 | Revise registration statement; underwriters' |  | All
| to | counsel to draft and distribute underwriter's
| 1999-02-10 | agreement, agreement among other underwriters,
selling agreement and other documents relating
to underwriting ("underwriting document") to
company counsel.
| 1999-02-11 | Distribution of second draft of registration statement. |  | XYZ, CC
| 1999-02-15 | Second drafting session to review registration |  | All
| and | statement
1999-02-16
| 1999-02-16 | Questionnaires completed by officers, directors, |  | XYZ
| to | and 10% shareholders and returned to company
| 1999-03-02 | counsel for review.
| 1999-02-17 | Distribution of third draft of registration statement. |  | XYZ, CC
| 1999-02-17 | Distribution of mangement's discussion and analysis |  | XYZ, A
of financial position and results of operations.
| 1999-02-19 | Board of directors meeting
Review offering.
Corporate housekeeping.
Authorize preparation and filing of registration
statement.
| 1999-02-22 | Third drafting session to review registration statement. |  | All
to
1999-02-23
| Date | Activity | Responsibility
| 1999-02-24 | Company counsel and underwriters' counsel meet |  | CC, UC
to discuss blue-sky problems and underwriting
documents.
| 1999-02-26 | Company counsel delivers draft of registration |  | CC
statement to printer for printing of red herring.
| 1999-03-01 | Audited financial statements available and provided to printer |  | XYZ, A
| 1999-03-02 | Printer's proofs of registration statement for review. |  | All
| 1999-03-02 | Board of directors' meeting to review registration statement; authorize blue-sky filings; appoint pricing committee; authorize other actions necessary to complete offering. |  | XYZ
| 1999-03-03 | All-hands meetings. |  | All
| to | Review printers proof of registration statements.
| 1999-03-04 | Discuss any discrepancies between text of
registration statement and financial statements.
Finalize underwriting documents.
| 1999-03-05 | Discuss items to include in accountant's comfort |  | U, UC, A
| to | letter.
1999-03-08
| 1999-03-08 | File Registration statement and exhibits with SEC. |  | XYZ, CC
| 1999-03-09 | Roadshow preparation. |  | XYZ, U
to
1999-03-23
| 1999-03-24 | Roadshow presentations to underwriters. |  | XYZ, U
to
1999-03-30
| 1999-03-31 | Roadshow |  | XYZ, U
to
1999-04-08
| 1999-04-06 | SEC Comments received. |  | All
to
1999-04-07
| 1999-04-07 | Appropriate changes made in registration statement or |  | All
| to | SEC comments otherwise addressed; miscellaneous
| 1999-04-08 | discussions with SEC staff regarding comments.
| 1999-04-08 | All-hands meeting to review first amendment to |  | All
registration statement; discuss other issues;
review underwriting agreement, etc.
| 1999-04-09 | File first amendment.
| 1999-04-14 | SEC comments on amendment, if any received. |  | CC, UC
| 1999-04-15 | Board of directors' pricing committee approves pricing and other filing matters. |  | XYZ, U
| 1999-04-21 | Second amendment (final pricing) filed with SEC; final prospectus printed. |  | CC, UC
| 1999-04-27 | CLOSING
Formulas:
Date = WORKDAY([Date, row above],6,H14)
Date = WORKDAY([Date, row above],2)

## IPO Timeline Reverse
IPO Timetable
| Date | Activity | Responsibility
| 1999-08-04 | Initial organization meeting and due dilligence |  | All
Review Timetable
Review letter of intent and discuss
underwriting issues.
Discuss Underwriters' fees and compensation
Assign registration statement preparation
responsibilities
Identify accounting and other problems.
Select Printer
Review financial forecasts
|  | Management due dilligence presentations. |  | All
Discuss transfer agent and registrar.
Prepare list of parties involved (phone numbers,
addresses, secretaries, etc.) referred to as
the working group list.
| 1999-08-18 | First draft of registration statement distributed. |  | All
| 1999-08-26 | First drafting session and due dilligence. |  | All
Complete due dilligence presentations.
Review draft of registration statement
Discuss problems
| 1999-08-26 | Revise registration statement; underwriters' |  | All
| to | counsel to draft and distribute underwriter's
| 1999-08-31 | agreement, agreement among other underwriters,
selling agreement and other documents relating
to underwriting ("underwriting document") to
company counsel.
| 1999-09-01 | Distribution of second draft of registration statement. |  | XYZ, CC
| 1999-09-03 | Second drafting session to review registration |  | All
| and | statement
1999-09-06
| 1999-09-06 | Questionnaires completed by officers, directors, |  | XYZ
| to | and 10% shareholders and returned to company
| 1999-09-20 | counsel for review.
| 1999-09-07 | Distribution of third draft of registration statement. |  | XYZ, CC
| 1999-09-07 | Distribution of mangement's discussion and analysis |  | XYZ, A
of financial position and results of operations.
| 1999-09-09 | Board of directors meeting
Review offering.
Corporate housekeeping.
Authorize preparation and filing of registration
statement.
| 1999-09-10 | Third drafting session to review registration statement. |  | All
to
1999-09-13
| Date | Activity | Responsibility
| 1999-09-14 | Company counsel and underwriters' counsel meet |  | CC, UC
to discuss blue-sky problems and underwriting
documents.
| 1999-09-16 | Company counsel delivers draft of registration |  | CC
statement to printer for printing of red herring.
| 1999-09-17 | Audited financial statements available and provided to printer |  | XYZ, A
| 1999-09-20 | Printer's proofs of registration statement for review. |  | All
| 1999-09-20 | Board of directors' meeting to review registration statement; authorize blue-sky filings; appoint pricing committee; authorize other actions necessary to complete offering. |  | XYZ
| 1999-09-21 | All-hands meetings. |  | All
| to | Review printers proof of registration statements.
| 1999-09-22 | Discuss any discrepancies between text of
registration statement and financial statements.
Finalize underwriting documents.
| 1999-09-23 | Discuss items to include in accountant's comfort |  | U, UC, A
| to | letter.
1999-09-24
| 1999-09-24 | File Registration statement and exhibits with SEC. |  | XYZ, CC
| 1999-09-27 | Roadshow preparation. |  | XYZ, U
to
1999-10-11
| 1999-10-12 | Roadshow presentations to underwriters. |  | XYZ, U
to
1999-10-18
| 1999-10-19 | Roadshow |  | XYZ, U
to
1999-10-27
| 1999-10-25 | SEC Comments received. |  | All
to
1999-10-26
| 1999-10-26 | Appropriate changes made in registration statement or |  | All
| to | SEC comments otherwise addressed; miscellaneous
| 1999-10-27 | discussions with SEC staff regarding comments.
| 1999-10-27 | All-hands meeting to review first amendment to |  | All
registration statement; discuss other issues;
review underwriting agreement, etc.
| 1999-10-28 | File first amendment.
| 1999-11-02 | SEC comments on amendment, if any received. |  | CC, UC
| 1999-11-03 | Board of directors' pricing committee approves pricing and other filing matters. |  | XYZ, U
| 1999-11-09 | Second amendment (final pricing) filed with SEC; final prospectus printed. |  | CC, UL
| 1999-11-14 | CLOSING
Formulas:
Date = WORKDAY([Date, row below],-6)